## CHECK
076551C-000S-MR | MR-1585-001
ANALYSER HOUSES PACKAGE
Bapco MR No | 000-J-MRQ-80018-001
Bapco PO No | 000-J-MPO-50105-001
Numerazione | MR-1585-001 - ABB SA
Disciplina | JV-VD INSTRUMENT._OUT---
Transmittal | 000-J-MRQ-80018-001 - ABB SA
SOC-JVD-VTRA | VENDOR DOCUMENTATION 000S- MR-1585-001
Bapco Doc No
Bapco Doc Rev
Equipment No
SR Doc Code
CDRL Code
Doc Class
Stamp
Matrix

## Counter
|  | 9:15 | 13:00 | 6:25 | 29 Transmittal | 7,25 Tempo Transmittal |  | 0 Rejected |  |  | 0 Tempo Rejected | 7,25 Ore totali
|  | 15:40 | 18:20 |  | 30 Documenti | 0.25 |  | 0 Doc Rejected |  |  | 0.5 | 30 Doc totali lavorati
CON-BMP-VTRA | [7 empty] | VTFT
1 | 1 | 098091 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098091 | 48781 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098091
2 | 2 | 098092 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098092 | 48782 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098092
3 | 2 | 098093 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098093 | 48783 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098093
4 | 2 | 098094 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098094 | 48784 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098094
5 | 2 | 098095 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098095 | 48785 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098095
6 | 2 | 098096 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098096 | 48786 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098096
7 | 1 | 098097 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098097 | 48787 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098097
8 | 1 | 098122 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098122 | 48820 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098122
9 | 1 | 098123 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098123 | 48821 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098124
10 | 1 | 098124 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098124 | 48822 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098125
11 | 1 | 098125 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098125 | 48823 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098126
12 | 1 | 098126 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098126 | 48824 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098129
13 | 1 | 098127 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098127 | 48850 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098165
14 | 1 | 098128 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098128 | 48851 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098166
15 | 1 | 098129 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098129 | 48852 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098167
16 | 1 | 098165 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098165 | 48853 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098168
17 | 2 | 098166 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098166 | 48854 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098171
18 | 2 | 098167 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098167
19 | 2 | 098168 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098168
20 | 1 | 098169 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098169
21 | 1 | 098170 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098170
22 | 1 | 098171 | G.SERRANI | 2020-12-01 | MR-1585-001 - ABB SA | SOC | CON-BMP-VTRA-098171
23 | [5 empty] | SOC | CON-BMP-VTRA-
24 | [5 empty] | SOC | CON-BMP-VTRA-
25 | [5 empty] | SOC | CON-BMP-VTRA-
26 | [5 empty] | SOC | CON-BMP-VTRA-
27 | [5 empty] | SOC | CON-BMP-VTRA-
28 | [5 empty] | SOC | CON-BMP-VTRA-
29 | [5 empty] | SOC | CON-BMP-VTRA- | REJECTED
[6 empty] | SOC | CON-BMP-VTRA- |  |  | DCC-SOC-EML-0
[6 empty] | SOC | CON-BMP-VTRA- |  |  | DCC-SOC-EML-0
[6 empty] | SOC | CON-BMP-VTRA- |  |  | DCC-SOC-EML-0
[6 empty] | SOC | CON-BMP-VTRA- |  |  | DCC-SOC-EML-0
[6 empty] | SOC | CON-BMP-VTRA- |  |  | DCC-SOC-EML-0
[6 empty] | SOC | CON-BMP-VTRA- |  |  | DCC-SOC-EML-0
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-
[6 empty] | SOC | CON-BMP-VTRA-

## Status
TR NUMBER | TR DATE | DOC. QTY | DESCRIPTION | ISSUED TO BAPCO | PENDING FROM SOC | PENDING ISSUE
|  |  |  | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-09 | PENDING BY SOC DCC-SOC-EML-0
SOC-JVD-VTRA-023032 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098091
SOC-JVD-VTRA-023033 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098092
SOC-JVD-VTRA-023034 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098093
SOC-JVD-VTRA-023035 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098094
SOC-JVD-VTRA-023036 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098095
SOC-JVD-VTRA-023039 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098096
SOC-JVD-VTRA-023041 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098097
SOC-JVD-VTRA-023053 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098122
SOC-JVD-VTRA-023054 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098123
SOC-JVD-VTRA-023055 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098124
SOC-JVD-VTRA-023056 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098125
SOC-JVD-VTRA-023057 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098126
SOC-JVD-VTRA-023063 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098127
SOC-JVD-VTRA-023064 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098128
SOC-JVD-VTRA-023065 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098129
SOC-JVD-VTRA-023072 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098165
SOC-JVD-VTRA-023073 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098166
SOC-JVD-VTRA-023074 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098167
SOC-JVD-VTRA-023075 | 2020-11-26 | 2 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098168
SOC-JVD-VTRA-023076 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098169
SOC-JVD-VTRA-023077 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098170
SOC-JVD-VTRA-023078 | 2020-11-26 | 1 | V/P FOR ANALYZER HOUSES PACKAGE | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-098171
SOC-JVD-VTRA-023099 | 2020-11-27 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023103 | 2020-11-27 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023108 | 2020-11-27 | 2 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023110 | 2020-11-27 | 2 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023111 | 2020-11-27 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023112 | 2020-11-27 | 1 | V/P FOR ANALYZER HOUSES PACKAGE |  | PENDING BY SOC DCC-SOC-EML-08337 | Red color
SOC-JVD-VTRA-023114 | 2020-11-27 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023115 | 2020-11-27 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023118 | 2020-11-30 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023130 | 2020-11-30 | 1 | V/P FOR ANALYZER HOUSES PACKAGE
SOC-JVD-VTRA-023131 | 2020-11-30 | 1 | V/P FOR ANALYZER HOUSES PACKAGE

## PO-LOI List
MR |  | DISCIPLINA |  |  | VENDOR | MRQ | PO | TITLE
MR | MR - VENDOR | JV-VD | MRQ - VENDOR | VENDOR DOCUMENTATION 000S- MR | VENDOR | MRQ | PO | TITLE
PROJECT MR No. | NUMERAZIONE | DISCIPLINE | TITLE TRANSMITTAL OUTGOING | DESCRIPTION ADMIN SOC-JVD-VTRA | VENDOR | BAPCO MR NO. | PO Number | MR Description | PO/LOA ISSUE DATE
MR-0113-001 | MR-0113-001 - TECHNIP STONE AND WEBSTER | JV-VD HEATERS & BOILERS_OUT--- | 000-F-MRQ-80001-001 - TECHNIP STONE AND WEBSTER | VENDOR DOCUMENTATION 000S- MR-0113-001 | TECHNIP STONE AND WEBSTER | 000-F-MRQ-80001-001 | JVENG000006-A | Steam Reformer | 2018-12-04
MR-0119-004 | MR-0119-004 - ZEECO INC | JV-VD HEATERS & BOILERS_OUT--- | 000-F-MRQ-80002-001 - ZEECO INC | VENDOR DOCUMENTATION 000S- MR-0119-004 | ZEECO INC | 000-F-MRQ-80002-001 | 000-F-MPO-50006-001 | SRU Reaction Furnace - Waste Heat Boiler and Steam Drum | 2018-11-13
MR-0140-001 | MR-0140-001 - ZEECO INC | JV-VD HEATERS & BOILERS_OUT--- | 000-F-MRQ-80003-001 - ZEECO INC | VENDOR DOCUMENTATION 000S- MR-0140-001 | ZEECO INC | 000-F-MRQ-80003-001 | 000-F-MPO-50007-001 | Incinerator Package | 2018-11-13
MR-0150-001 | MR-0150-001 - MACCHI | JV-VD HEATERS & BOILERS_OUT--- | 000-F-MRQ-80004-001 - MACCHI | VENDOR DOCUMENTATION 000S- MR-0150-001 | MACCHI | 000-F-MRQ-80004-001 | 000-F-MPO-50002-001 | Auxiliary Steam Boiler | 2018-10-05
MR-0213-001 | MR-0213-001 - ARTES INGEGNERIA | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80001-001 - ARTES INGEGNERIA | VENDOR DOCUMENTATION 000S- MR-0213-001 | ARTES INGEGNERIA | 000-S-MRQ-80001-001 | 000-S-MPO-50008-001 | Polishing Package | 2018-10-31
MR-0215-001 | MR-0215-001 - DOOSAN HEAVY INDUSTRIES & CONSTRUCTION | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80002-001 - DOOSAN HEAVY INDUSTRIES & CONSTRUCTION | VENDOR DOCUMENTATION 000S- MR-0215-001 | DOOSAN HEAVY INDUSTRIES & CONSTRUCTION | 000-S-MRQ-80002-001 | 000-S-MPO-50004-001 | Multi-Effect Desalination Package | 2018-09-28
MR-0411-001 | MR-0411-001 - HANTECH LTD | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80004-001 - HANTECH LTD | VENDOR DOCUMENTATION 000S- MR-0411-001 | HANTECH LTD | 000-C-MRQ-80004-001 | 000-C-MPO-50014-001 | Reactors | 2018-10-17
MR-0510-001 | MR-0510-001 - POWER HX TECH | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80005-001 - POWER HX TECH | VENDOR DOCUMENTATION 000S- MR-0510-001 | POWER HX TECH | 000-C-MRQ-80005-001 | 000-C-MPO-50018-001 | Deaerator | 2018-11-02
MR-0511-001 | MR-0511-001 - GS ENTEC CORPORATION | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80006-001 - GS ENTEC CORPORATION | VENDOR DOCUMENTATION 000S- MR-0511-001 | GS ENTEC CORPORATION | 000-C-MRQ-80006-001 | 000-C-MPO-50010-001 | CS Columns | 2018-10-10
MR-0511-002 | MR-0511-002 - GS ENTEC CORPORATION | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80007-001 - GS ENTEC CORPORATION | VENDOR DOCUMENTATION 000S- MR-0511-002 | GS ENTEC CORPORATION | 000-C-MRQ-80007-001 | 000-C-MPO-50011-001 | CLADDED COLUMNS | 2018-10-11
MR-0570-001 | MR-0570-001 - GTC TECHNOLOGY KOREA CO LTD | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80008-001 - GTC TECHNOLOGY KOREA CO LTD | VENDOR DOCUMENTATION 000S- MR-0570-001 | GTC TECHNOLOGY KOREA CO LTD | 000-C-MRQ-80008-001 | 000-C-MPO-50016-001 | Trays and Internals for Columns | 2018-10-24
MR-0610-002 | MR-0610-002 - GODREJ & BOYCE MFG. CO. | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80001-001 - GODREJ & BOYCE MFG. CO. | VENDOR DOCUMENTATION 000S- MR-0610-002 | GODREJ & BOYCE MFG. CO. | 000-E-MRQ-80001-001 | 000-E-MPO-50008-001 | Clad Shell and Tube Heat Exchangers | 2018-10-24
MR-0610-003 | MR-0610-003 - CURO CO LTD | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80002-001 - CURO CO LTD | VENDOR DOCUMENTATION 000S- MR-0610-003 | CURO CO LTD | 000-E-MRQ-80002-001 | 000-E-MPO-50013-001 | Wet H2S and Special Service CS Shell and Tube Heat Exchangers | 2018-11-14
MR-0610-004 | MR-0610-004 - CURO CO LTD | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80003-001 - CURO CO LTD | VENDOR DOCUMENTATION 000S- MR-0610-004 | CURO CO LTD | 000-E-MRQ-80003-001 | 000-E-MPO-50016-001 | Carbon Steel Heat Exchangers | 2018-11-14
MR-0610-005 | MR-0610-005 - CURO CO LTD | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80004-001 - CURO CO LTD | VENDOR DOCUMENTATION 000S- MR-0610-005 | CURO CO LTD | 000-E-MRQ-80004-001 | 000-E-MPO-50010-001 | Sulphur Condenser | 2018-11-14
MR-0610-006 | MR-0610-006 - VAHTERUS OY | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80008-001 - VAHTERUS OY | VENDOR DOCUMENTATION 000S- MR-0610-006 | VAHTERUS OY | 000-E-MRQ-80008-001 | 000-E-MPO-50020-001 | Plate and Shell Heat Exchanger | 2019-01-31
MR-0660-001 | MR-0660-001 - LHE CO LTD | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80006-001 - LHE CO LTD | VENDOR DOCUMENTATION 000S- MR-0660-001 | LHE CO LTD | 000-E-MRQ-80006-001 | 000-E-MPO-50009-001 | Plate and Frame Heat Exchangers | 2018-11-14
MR-0710-002 | MR-0710-002 - Korea Heat Exchanger | JV-VD PRESSURE EQPT_OUT--- | - Korea Heat Exchanger | VENDOR DOCUMENTATION 000S- MR-0710-002 | Korea Heat Exchanger |  | 000-E-MPO-50001-001 | Air Coolers | 2018-10-04
MR-0710-102 | MR-0710-102 - DASAN THERMAL SOLUTIONS IND. | JV-VD PRESSURE EQPT_OUT--- | 000-E-MRQ-80005-001 - DASAN THERMAL SOLUTIONS IND. | VENDOR DOCUMENTATION 000S- MR-0710-102 | DASAN THERMAL SOLUTIONS IND. | 000-E-MRQ-80005-001 | 000-E-MPO-50030-001 | Air Coolers | 2019-08-23
MR-0811-002 | MR-0811-002 - ULP | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80001-001 - ULP | VENDOR DOCUMENTATION 000S- MR-0811-002 | ULP | 000-C-MRQ-80001-001 | 000-C-MPO-50025-001 | Stainless Steel and Clad Vessels | 2018-11-29
MR-0811-003 | MR-0811-003 - UBEC INC | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80003-001 - UBEC INC | VENDOR DOCUMENTATION 000S- MR-0811-003 | UBEC INC | 000-C-MRQ-80003-001 | 000-C-MPO-50022-001 | CS Vessel below 19 mm Thickness / 20 tons | 2018-11-23
MR-0811-004 | MR-0811-004 - WOOYANG HC CO. LTD | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80013-001 - WOOYANG HC CO. LTD | VENDOR DOCUMENTATION 000S- MR-0811-004 | WOOYANG HC CO. LTD | 000-C-MRQ-80013-001 | 000-C-MPO-50023-001 | CS Vessel above 19 mm Thickness / 20 tons | 2018-11-23
MR-0836-001 | MR-0836-001 - STOPSON ITALIANA S.R.L. | JV-VD PACKAGE UNIT_OUT--- | 000-C-MRQ-80012-001 - STOPSON ITALIANA S.R.L. | VENDOR DOCUMENTATION 000S- MR-0836-001 | STOPSON ITALIANA S.R.L. | 000-C-MRQ-80012-001 | 000-C-MPO-50051-001 | Silencers | 2019-08-20
MR-0836-002 | MR-0836-002 - STOPSON ITALIANA S.R.L. | Discipline: PIPING MATERIAL MANAGEMENT SOC-304S Matrix: JV-VD PACKAGE UNIT | 000-L-MRQ-80002-001 - STOPSON ITALIANA S.R.L. | VENDOR DOCUMENTATION 000S- MR-0836-002 | STOPSON ITALIANA S.R.L. | 000-L-MRQ-80002-001 | 000-L-MPO-50068-001 | NON-PROCESS SILENCERS | 2020-06-09
MR-0841-001 | MR-0841-001 - BEA TECHNOLOGIES SPA | JV-VD PACKAGE UNIT_OUT--- | 000-C-MRQ-80009-001 - BEA TECHNOLOGIES SPA | VENDOR DOCUMENTATION 000S- MR-0841-001 | BEA TECHNOLOGIES SPA | 000-C-MRQ-80009-001 | 000-C-MPO-50035-001 | Filters | 2019-01-15
MR-0841-002 | MR-0841-002 - PARKER KOREA | JV-VD PACKAGE UNIT_OUT--- | 000-C-MRQ-80010-001 - PARKER KOREA | VENDOR DOCUMENTATION 000S- MR-0841-002 | PARKER KOREA | 000-C-MRQ-80010-001 | 000-C-MPO-50028-001 | Coalescers | 2018-12-10
MR-0841-003 | MR-0841-003 - CONTROLS SOUTHEAST INC | JV-VD PACKAGE UNIT_OUT--- | 000-C-MRQ-80011-001 - CONTROLS SOUTHEAST INC | VENDOR DOCUMENTATION 000S- MR-0841-003 | CONTROLS SOUTHEAST INC | 000-C-MRQ-80011-001 | 000-C-MPO-50034-001 | Sulphur Locks | 2018-12-20
MR-0841-004 | MR-0841-004 - HOWE BAKER ENGINEERS | JV-VD PACKAGE UNIT_OUT--- | 000-C-MRQ-80014-001 - HOWE BAKER ENGINEERS | VENDOR DOCUMENTATION 000S- MR-0841-004 | HOWE BAKER ENGINEERS | 000-C-MRQ-80014-001 | 000-C-MPO-50048-001 | Electrostatic Coalescers | 2019-05-31
MR-0848-001 | MR-0848-001 - CDB ENGINEERING SPA | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80011-001 - CDB ENGINEERING SPA | VENDOR DOCUMENTATION 000S- MR-0848-001 | CDB ENGINEERING SPA | 000-S-MRQ-80011-001 | 000-S-MPO-50016-001 | FEED Strainers | 2018-12-17
MR-0852-001 | MR-0852-001 - SAMWON ENGINEERING CO. LTD | JV-VD PACKAGE UNIT_OUT--- | 000-L-MRQ-80001-001 - SAMWON ENGINEERING CO. LTD | VENDOR DOCUMENTATION 000S- MR-0852-001 | SAMWON ENGINEERING CO. LTD | 000-L-MRQ-80001-001 | 000-L-MPO-50016-001 | Desuperheaters | 2018-12-14
MR-0852-002 | MR-0852-002 - SAMWON ENGINEERING CO. LTD | JV-VD PACKAGE UNIT_OUT--- | 000-H-MRQ-80002-001 - SAMWON ENGINEERING CO. LTD | VENDOR DOCUMENTATION 000S- MR-0852-002 | SAMWON ENGINEERING CO. LTD | 000-H-MRQ-80002-001 | 000-H-MPO-50003-001 | Ejectors | 2018-12-14
MR-0910-002 | MR-0910-002 - ITT GOULDS PUMPS | JV-VD MACHINERY_OUT--- | 000-G-MRQ-80002-001 - ITT GOULDS PUMPS | VENDOR DOCUMENTATION 000S- MR-0910-002 | ITT GOULDS PUMPS | 000-G-MRQ-80002-001 | 000-G-MPO-50008-001 | ASME Pumps | 2019-02-01
MR-0910-003 | MR-0910-003 - TRILLIUM | JV-VD MACHINERY_OUT--- | 000-G-MRQ-80003-001 - TRILLIUM | VENDOR DOCUMENTATION 000S- MR-0910-003 | TRILLIUM | 000-G-MRQ-80003-001 | 000-G-MPO-50009-001 | BB1, BB2 and BB3 Pumps | 2019-02-19
MR-0910-006 | MR-0910-006 - KSB SE + CO. KGAa | JV-VD MACHINERY_OUT--- | 000-G-MRQ-80004-001 - KSB SE + CO. KGAa | VENDOR DOCUMENTATION 000S- MR-0910-006 | KSB SE + CO. KGAa | 000-G-MRQ-80004-001 | 000-G-MPO-50010-001 | Vertical Pumps | 2019-02-20
MR-0910-007 | MR-0910-007 - WEIR PUMP | JV-VD MACHINERY_OUT--- | 000-G-MRQ-80005-001 - WEIR PUMP | VENDOR DOCUMENTATION 000S- MR-0910-007 | WEIR PUMP | 000-G-MRQ-80005-001 | 000-G-MPO-50006-001 | Sulphur Tranfer Pumps | 2019-01-11
MR-0910-013 | MR-0910-013 - THE GORMAN-RUPP | JV-VD MACHINERY_OUT--- | 000-G-MRQ-80008-001 - THE GORMAN-RUPP | VENDOR DOCUMENTATION 000S- MR-0910-013 | THE GORMAN-RUPP | 000-G-MRQ-80008-001 | 000-G-MPO-50033-001 | SANITARY PUMPS
MR-0910-101 | MR-0910-101 - WORTHINGTON SRL | JV-VD MACHINERY_OUT--- | 000-G-MRQ-80007-001 - WORTHINGTON SRL | VENDOR DOCUMENTATION 000S- MR-0910-101 | WORTHINGTON SRL | 000-G-MRQ-80007-001 | 000-G-MPO-50012-001 | API 610 Centrifugal Pumps | 2019-02-21
MR-1013-001 | MR-1013-001 - HANWHA POWER SYSTEMS | JV-VD MACHINERY_OUT--- | 000-K-MRQ-80003-001 - HANWHA POWER SYSTEMS | VENDOR DOCUMENTATION 000S- MR-1013-001 | HANWHA POWER SYSTEMS | 000-K-MRQ-80003-001 | 000-K-MPO-50009-001 | IG Air Compressors | 2019-02-01
MR-1020-001 | MR-1020-001 - KOBE STEEL LTD | JV-VD MACHINERY_OUT--- | 000-K-MRQ-80001-001 - KOBE STEEL LTD | VENDOR DOCUMENTATION 000S- MR-1020-001 | KOBE STEEL LTD | 000-K-MRQ-80001-001 | 000-K-MPO-50001-001 | Reciprocating Compressors (API 618) | 2018-11-16
MR-1020-002 | MR-1020-002 - GTC CO LTD | JV-VD MACHINERY_OUT--- | 000-K-MRQ-80002-001 - GTC CO LTD | VENDOR DOCUMENTATION 000S- MR-1020-002 | GTC CO LTD | 000-K-MRQ-80002-001 | 000-K-MPO-50016-001 | Reciprocating Compressor (General Service) | 2019-03-29
MR-1040-001 | MR-1040-001 - BOLDROCCHI SRL | JV-VD MACHINERY_OUT--- | 000-K-MRQ-80004-001 - BOLDROCCHI SRL | VENDOR DOCUMENTATION 000S- MR-1040-001 | BOLDROCCHI SRL | 000-K-MRQ-80004-001 | 000-K-MPO-50011-001 | Fan and Blower | 2019-02-15
MR-1541-001 | MR-1541-001 - GE OIL AND GAS INDIA | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80002-001 - GE OIL AND GAS INDIA | VENDOR DOCUMENTATION 000S- MR-1541-001 | GE OIL AND GAS INDIA | 000-J-MRQ-80002-001 | 000-J-MPO-50039-001 | Control Valves and Self Actuated Valves | 2019-07-12
MR-1541-002 | MR-1541-002 - DRESSER | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80003-001 - DRESSER | VENDOR DOCUMENTATION 000S- MR-1541-002 | DRESSER | 000-J-MRQ-80003-001 | 000-J-MPO-50013-001 | Severe Service Control Valves | 2019-05-30
MR-1541-101 | MR-1541-101 - EMERSON | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80040-001 - EMERSON | VENDOR DOCUMENTATION 000S- MR-1541-101 | EMERSON | 000-J-MRQ-80040-001 | 000-J-MPO-50029-001 | Control Valves and Self Actuated Valves | 2019-07-19
MR-1542-002 | MR-1542-002 - IMI CCI ITALY SRL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80006-001 - IMI CCI ITALY SRL | VENDOR DOCUMENTATION 000S- MR-1542-002 | IMI CCI ITALY SRL | 000-J-MRQ-80006-001 | 000-J-MPO-50003-001 | Severe Desuperheater Control Valves | 2019-03-29
MR-1543-001 | MR-1543-001 - CUNADO | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80026-001 - CUNADO | VENDOR DOCUMENTATION 000S- MR-1543-001 | CUNADO | 000-J-MRQ-80026-001 | 000-J-MPO-50041-001 | ON-OFF Ball Valves | 2019-07-26
MR-1543-002 | MR-1543-002 - ORTON | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80027-001 - ORTON | VENDOR DOCUMENTATION 000S- MR-1543-002 | ORTON | 000-J-MRQ-80027-001 | 000-J-MPO-50001-001 | ON-OFF Butterfly Valves (Pneumatic/Electric/Hydraulic Actuator) | 2019-02-22
MR-1543-101 | MR-1543-101 - EMERSON | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80041-001 - EMERSON | VENDOR DOCUMENTATION 000S- MR-1543-101 | EMERSON | 000-J-MRQ-80041-001 | 000-J-MPO-50043-001 | ON-OFF Ball Valves | 2019-07-23
MR-1543-201 | MR-1543-201 - FLOWSERVE | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80042-001 - FLOWSERVE | VENDOR DOCUMENTATION 000S- MR-1543-201 | FLOWSERVE | 000-J-MRQ-80042-001 | 000-J-MPO-50044-001 | ON-OFF Ball Valves | 2019-07-19
MR-1545-001 | MR-1545-001 - DRESSER LLC. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80004-001 - DRESSER LLC. | VENDOR DOCUMENTATION 000S- MR-1545-001 | DRESSER LLC. | 000-J-MRQ-80004-001 | 000-J-MPO-50002-001 | Safety Relief Valves and Rupture Risk | 2019-03-08
MR-1546-001 | MR-1546-001 - SAMIL INDUSTRY CO. LTD. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80005-001 - SAMIL INDUSTRY CO. LTD. | VENDOR DOCUMENTATION 000S- MR-1546-001 | SAMIL INDUSTRY CO. LTD. | 000-J-MRQ-80005-001 | 000-J-MPO-50045-001 | Orifice Plate, Restriction Orifice and Venturi | 2019-08-02
MR-1546-002 | MR-1546-002 - WIKA ITALIA SRL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80017-001 - WIKA ITALIA SRL | VENDOR DOCUMENTATION 000S- MR-1546-002 | WIKA ITALIA SRL | 000-J-MRQ-80017-001 | 000-J-MPO-50016-001 | Pitot and Averaging Pitot | 2019-06-26
MR-1546-003 | MR-1546-003 - EMERSON PROCESS MANAGEMENT S.R.L | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80043-001 - EMERSON PROCESS MANAGEMENT S.R.L | VENDOR DOCUMENTATION 000S- MR-1546-003 | EMERSON PROCESS MANAGEMENT S.R.L | 000-J-MRQ-80043-001 | 000-J-MPO-50116-001 | MATERIAL REQUISITION FOR MULTIHOLE ORIFICE PLATE
MR-1547-002 | MR-1547-002 - EMERSON | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80007-001 - EMERSON | VENDOR DOCUMENTATION 000S- MR-1547-002 | EMERSON | 000-J-MRQ-80007-001 | 000-J-MPO-50012-001 | Rotameters | 2019-04-24
MR-1547-004 | MR-1547-004 - MAGNETROL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80008-001 - MAGNETROL | VENDOR DOCUMENTATION 000S- MR-1547-004 | MAGNETROL | 000-J-MRQ-80008-001 | 000-J-MPO-50015-001 | Thermal Mass Flowmeter | 2019-05-02
MR-1547-005 | MR-1547-005 - EMERSON PROCESS MANAGEMENT S.R.L | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80010-001 - EMERSON PROCESS MANAGEMENT S.R.L | VENDOR DOCUMENTATION 000S- MR-1547-005 | EMERSON PROCESS MANAGEMENT S.R.L | 000-J-MRQ-80010-001 | 000-J-MPO-50011-001 | Electromagnetic Flowmeter | 2019-04-24
MR-1547-007 | MR-1547-007 - BAKER HUGHES DIGITAL SOLUTIONS ITALIA S.r.l. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80012-001 - BAKER HUGHES DIGITAL SOLUTIONS ITALIA S.r.l. | VENDOR DOCUMENTATION 000S- MR-1547-007 | BAKER HUGHES DIGITAL SOLUTIONS ITALIA S.r.l. | 000-J-MRQ-80012-001 | 000-J-MPO-50059-001 | Ultrasonic Flowmeters | 2019-10-04
MR-1552-001 | MR-1552-001 - SAMIL INDUSTRY CO. LTD. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80019-001 - SAMIL INDUSTRY CO. LTD. | VENDOR DOCUMENTATION 000S- MR-1552-001 | SAMIL INDUSTRY CO. LTD. | 000-J-MRQ-80019-001 | 000-J-MPO-50061-001 | Level Glass and Magnetic Level Gauge | 2019-10-03
MR-1552-002 | MR-1552-002 - EMERSON PROCESS MANAGEMENT S.R.L | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80020-001 - EMERSON PROCESS MANAGEMENT S.R.L | VENDOR DOCUMENTATION 000S- MR-1552-002 | EMERSON PROCESS MANAGEMENT S.R.L | 000-J-MRQ-80020-001 | 000-J-MPO-50072-001 | Radar Level Instruments | 2019-09-30
MR-1553-001 | MR-1553-001 - YOKOGAWA ITALIA SRL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80014-001 - YOKOGAWA ITALIA SRL | VENDOR DOCUMENTATION 000S- MR-1553-001 | YOKOGAWA ITALIA SRL | 000-J-MRQ-80014-001 | 000-J-MPO-50098-001 | ELECTRONIC TRANSMITTERS
MR-1553-002 | MR-1553-002 - WISE CONTROL INC. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80021-001 - WISE CONTROL INC. | VENDOR DOCUMENTATION 000S- MR-1553-002 | WISE CONTROL INC. | 000-J-MRQ-80021-001 | 000-J-MPO-50065-001 | Pressure and Differential Pressure Gauges | 2019-10-04
MR-1553-003 | MR-1553-003 - YOKOGAWA ITALIA SRL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80009-001 - YOKOGAWA ITALIA SRL | VENDOR DOCUMENTATION 000S- MR-1553-003 | YOKOGAWA ITALIA SRL | 000-J-MRQ-80009-001 | 000-J-MPO-50120-001 | WIRELESS TRANSMITTERS
MR-1554-001 | MR-1554-001 - RUEGER | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80023-001 - RUEGER | VENDOR DOCUMENTATION 000S- MR-1554-001 | RUEGER | 000-J-MRQ-80023-001 | 000-J-MPO-50084-001 | Thermocouple/RTD with Well | 2019-10-31
MR-1554-002 | MR-1554-002 - TM TECNOMATIC SRL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80015-001 - TM TECNOMATIC SRL | VENDOR DOCUMENTATION 000S- MR-1554-002 | TM TECNOMATIC SRL | 000-J-MRQ-80015-001 | 000-J-MPO-50050-001 | Multiple Thermocouples | 2019-08-23
MR-1554-003 | MR-1554-003 - TEMA SRL | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80022-001 - TEMA SRL | VENDOR DOCUMENTATION 000S- MR-1554-003 | TEMA SRL | 000-J-MRQ-80022-001 | 000-J-MPO-50086-001 | Thermometers with Well | 2019-11-22
MR-1554-004 | MR-1554-004 - DELTA CONTROLS CORPORATION | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80029-001 - DELTA CONTROLS CORPORATION | VENDOR DOCUMENTATION 000S- MR-1554-004 | DELTA CONTROLS CORPORATION | 000-J-MRQ-80029-001 | 000-J-MPO-50023-001 | Pyrometers | 2019-06-28
MR-1554-005 | MR-1554-005 - DELTA CONTROLS CORPORATION | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80044-001 - DELTA CONTROLS CORPORATION | VENDOR DOCUMENTATION 000S- MR-1554-005 | DELTA CONTROLS CORPORATION | 000-J-MRQ-80044-001 | 000-J-MPO-50114-001 | THERMOCOUPLE AT REACTION FURNACE
MR-1562-001 | MR-1562-001 - SOCRATE S.P.A | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80001-001 - SOCRATE S.P.A | VENDOR DOCUMENTATION 000S- MR-1562-001 | SOCRATE S.P.A | 000-J-MRQ-80001-001 | 000-J-MPO-50136-001 | SULPHUR ANALYSERS
MR-1562-101 | MR-1562-101 - TYCO FIRE AND SEC. UAE LLC | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80049-001 - TYCO FIRE AND SEC. UAE LLC | VENDOR DOCUMENTATION 000S- MR-1562-101 | TYCO FIRE AND SEC. UAE LLC | 000-J-MRQ-80049-001 | 000-J-MPO-50137-001 | SULPHUR ANALYSERS
MR-1564-001 | MR-1564-001 - ENDRESS+HAUSER | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80011-001 - ENDRESS+HAUSER | VENDOR DOCUMENTATION 000S- MR-1564-001 | ENDRESS+HAUSER | 000-J-MRQ-80011-001 | 000-J-MPO-50079-001 | Water Analysers | 2019-10-11
MR-1565-001 | MR-1565-001 - SIEMENS S.P.A. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80013-001 - SIEMENS S.P.A. | VENDOR DOCUMENTATION 000S- MR-1565-001 | SIEMENS S.P.A. | 000-J-MRQ-80013-001 | 000-J-MPO-50108-001
MR-1566-001 | MR-1566-001 - DRAGER SAFETY AG & CO. KGAA | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80016-001 - DRAGER SAFETY AG & CO. KGAA | VENDOR DOCUMENTATION 000S- MR-1566-001 | DRAGER SAFETY AG & CO. KGAA | 000-J-MRQ-80016-001 | 000-J-MPO-50080-001 | Fire and Gas Detectors | 2019-10-18
MR-1566-101 | MR-1566-101 - GASTRON.,CO.LTD | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80045-001 - GASTRON.,CO.LTD | VENDOR DOCUMENTATION 000S- MR-1566-101 | GASTRON.,CO.LTD | 000-J-MRQ-80045-001 | 000-J-MPO-50081-001 | Fire and Gas Detectors | 2019-10-18
MR-1572-001 | MR-1572-001 - IBERFLUID INSTRUMENTS, S.A. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80034-001 - IBERFLUID INSTRUMENTS, S.A. | VENDOR DOCUMENTATION 000S- MR-1572-001 | IBERFLUID INSTRUMENTS, S.A. | 000-J-MRQ-80034-001 | 000-J-MPO-50132-001 | MATERIAL REQUISITION FOR MOUNTING ACCESSORIES (TUBING AND FITTINGS)
MR-1572-005 | MR-1572-005 - ABB SA | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80037-001 - ABB SA | VENDOR DOCUMENTATION 000S- MR-1572-005 | ABB SA | 000-J-MRQ-80037-001 | 000-J-MPO-50112-001 | MULTI CABLE TRANSIT (MCT)
MR-1572-101 | MR-1572-101 - ARCAMO CONTROLS S. A. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80048-001 - ARCAMO CONTROLS S. A. | VENDOR DOCUMENTATION 000S- MR-1572-101 | ARCAMO CONTROLS S. A. | 000-J-MRQ-80048-001 | 000-J-MPO-50133-001 | MATERIAL REQUISITION FOR MOUNTING ACCESSORIES (TUBING AND FITTINGS)
MR-1574-001 | MR-1574-001 - MIDDLE EAST SPEC. CABLES CO. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80038-001 - MIDDLE EAST SPEC. CABLES CO. | VENDOR DOCUMENTATION 000S- MR-1574-001 | MIDDLE EAST SPEC. CABLES CO. | 000-J-MRQ-80038-001 | 000-J-MPO-50128-001 | CABLE, MULTICABLE AND FIBER OPTIC CABLE
MR-1575-001 | MR-1575-001 - COMAPLE S.L. | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80039-001 - COMAPLE S.L. | VENDOR DOCUMENTATION 000S- MR-1575-001 | COMAPLE S.L. | 000-J-MRQ-80039-001 | 000-J-MPO-50134-001 | MATERIAL REQUISITION FOR JUNCTION BOXE - CABLE GLAND - PUSH BUTTON AND HAND SW
MR-1585-001 | MR-1585-001 - ABB SA | JV-VD INSTRUMENT._OUT--- | 000-J-MRQ-80018-001 - ABB SA | VENDOR DOCUMENTATION 000S- MR-1585-001 | ABB SA | 000-J-MRQ-80018-001 | 000-J-MPO-50105-001 | ANALYSER HOUSES PACKAGE
MR-1628-001 | MR-1628-001 - CORTEM | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80001-001 - CORTEM | VENDOR DOCUMENTATION 000S- MR-1628-001 | CORTEM | 000-P-MRQ-80001-001 | 000-P-MPO-50017-001 | LV Indoor Distribution Panel Boards | 2019-03-29
MR-1628-002 | MR-1628-002 - VIMEX | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80011-001 - VIMEX | VENDOR DOCUMENTATION 000S- MR-1628-002 | VIMEX | 000-P-MRQ-80011-001 | 000-P-MPO-50021-001 | Switchrack on Revamped Areas | 2019-04-19
MR-1641-001 | MR-1641-001 - SCHNEIDER ELECTRIC | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80002-001 - SCHNEIDER ELECTRIC | VENDOR DOCUMENTATION 000S- MR-1641-001 | SCHNEIDER ELECTRIC | 000-P-MRQ-80002-001 | 000-P-MPO-50003-001 | Power/Distribution Transformers and Neutral Grounding Resistors | 2019-02-05
MR-1652-001 | MR-1652-001 - L&T ELECTRICAL & AUTOMATION | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80003-001 - L&T ELECTRICAL & AUTOMATION | VENDOR DOCUMENTATION 000S- MR-1652-001 | L&T ELECTRICAL & AUTOMATION | 000-P-MRQ-80003-001 | 000-P-MPO-50002-001 | HV Switchgear | 2019-02-08
MR-1653-001 | MR-1653-001 - ETA-COM UK PREEDCREET LIMITED | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80004-001 - ETA-COM UK PREEDCREET LIMITED | VENDOR DOCUMENTATION 000S- MR-1653-001 | ETA-COM UK PREEDCREET LIMITED | 000-P-MRQ-80004-001 | 000-P-MPO-50007-001 | HV and LV Bus Duct | 2019-02-22
MR-1654-001 | MR-1654-001 - WECOSA | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80005-001 - WECOSA | VENDOR DOCUMENTATION 000S- MR-1654-001 | WECOSA | 000-P-MRQ-80005-001 | 000-P-MPO-50001-001 | LV Switchgears | 2019-02-08
MR-1654-002 | MR-1654-002 - POWELL UK LIMITED | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80009-001 - POWELL UK LIMITED | VENDOR DOCUMENTATION 000S- MR-1654-002 | POWELL UK LIMITED | 000-P-MRQ-80009-001 | 000-P-MPO-50027-001 | Revamping of LV Switchgears | 2019-05-08
MR-1656-001 | MR-1656-001 - CIRCUTOR | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80006-001 - CIRCUTOR | VENDOR DOCUMENTATION 000S- MR-1656-001 | CIRCUTOR | 000-P-MRQ-80006-001 | 000-P-MPO-50009-001 | HV Capacitor Banks | 2019-02-22
MR-1671-001 | MR-1671-001 - BORRI SPA | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80007-001 - BORRI SPA | VENDOR DOCUMENTATION 000S- MR-1671-001 | BORRI SPA | 000-P-MRQ-80007-001 | 000-P-MPO-50014-001 | AC and DC UPS System | 2019-03-21
MR-1682-001 | MR-1682-001 - THERMON UK LTD | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80010-001 - THERMON UK LTD | VENDOR DOCUMENTATION 000S- MR-1682-001 | THERMON UK LTD | 000-P-MRQ-80010-001 | 000-P-MPO-50031-001 | Electrical Heat Tracing | 2019-06-14
MR-1800-001 | MR-1800-001 - ZAMIL STRUCTURAL STEEL COMPANY LTD | JV-VD CIVIL | 000-M-MRQ-80001-001 - ZAMIL STRUCTURAL STEEL COMPANY LTD | VENDOR DOCUMENTATION 000S- MR-1800-001 | ZAMIL STRUCTURAL STEEL COMPANY LTD | 000-M-MRQ-80001-001 | 000-M-MPO-50005-001 | Steel Structures | 2019-03-07
MR-1820-001 | MR-1820-001 - AL-A ALI | JV-VD PRESSURE EQPT_OUT--- | 000-M-MRQ-80002-001 - AL-A ALI | VENDOR DOCUMENTATION 000S- MR-1820-001 | AL-A ALI | 000-M-MRQ-80002-001 | 000-M-MPO-50009-001 | Ladders And Platforms | 2019-08-13
MR-2410-001 | MR-2410-001 - CATHODIC PROTECTION CO LTD | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80008-001 - CATHODIC PROTECTION CO LTD | VENDOR DOCUMENTATION 000S- MR-2410-001 | CATHODIC PROTECTION CO LTD | 000-P-MRQ-80008-001 | 000-P-MPO-50026-001 | Cathodic Protection System | 2019-04-26
MR-2520-001 | MR-2520-001 - HIDADA LTD | JV-VD PRESSURE EQPT_OUT--- | 000-D-MRQ-80001-001 - HIDADA LTD | VENDOR DOCUMENTATION 000S- MR-2520-001 | HIDADA LTD | 000-D-MRQ-80001-001 | 000-D-MPO-50002-001 | Storage Tanks | 2019-05-31
MR-2543-001 | MR-2543-001 - DOOSAN MECATEC | JV-VD PRESSURE EQPT_OUT--- | 000-C-MRQ-80002-001 - DOOSAN MECATEC | VENDOR DOCUMENTATION 000S- MR-2543-001 | DOOSAN MECATEC | 000-C-MRQ-80002-001 | 000-C-MPO-50027-001 | Storage Bullets | 2018-12-06
MR-4010-001 | MR-4010-001 - MOTRIDAL | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80003-001 - MOTRIDAL | VENDOR DOCUMENTATION 000S- MR-4010-001 | MOTRIDAL | 000-S-MRQ-80003-001 | 000-S-MPO-50006-001 | BMP Solid Sulphur Handling Package | 2018-09-28
MR-4041-001 | MR-4041-001 - MAPOSCALE CO. LTD | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80004-001 - MAPOSCALE CO. LTD | VENDOR DOCUMENTATION 000S- MR-4041-001 | MAPOSCALE CO. LTD | 000-S-MRQ-80004-001 | 000-S-MPO-50018-001 | Truck Scale Weighing Bridge | 2019-02-22
MR-4046-001 | MR-4046-001 - FORES ENGINEERING | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80005-001 - FORES ENGINEERING | VENDOR DOCUMENTATION 000S- MR-4046-001 | FORES ENGINEERING | 000-S-MRQ-80005-001 | 000-S-MPO-50009-001 | Dosing System | 2018-11-22
MR-4065-001 | MR-4065-001 - MELONI TECNO-HANDLING | JV-VD PACKAGE UNIT_OUT--- | 000-K-MRQ-80006-001 - MELONI TECNO-HANDLING | VENDOR DOCUMENTATION 000S- MR-4065-001 | MELONI TECNO-HANDLING | 000-K-MRQ-80006-001 | 000-K-MPO-50014-001 | Bridge Cranes | 2019-03-22
MR-4111-001 | MR-4111-001 - LINDE AG | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80007-001 - LINDE AG | VENDOR DOCUMENTATION 000S- MR-4111-001 | LINDE AG | 000-S-MRQ-80007-001 | 000-S-MPO-50015-001 | Hydrogen PSA Unit | 2018-12-14
MR-4112-001 | MR-4112-001 - SIAD MACCHINE IMPIANTI | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80008-001 - SIAD MACCHINE IMPIANTI | VENDOR DOCUMENTATION 000S- MR-4112-001 | SIAD MACCHINE IMPIANTI | 000-S-MRQ-80008-001 | 000-S-MPO-50012-001 | Nitrogen Generation, Storage and Vaporization Package | 2018-11-12
MR-4123-001 | MR-4123-001 - INTERNACO SA | JV-VD ELECTRICAL_OUT--- | 000-P-MRQ-80012-001 - INTERNACO SA | VENDOR DOCUMENTATION 000S- MR-4123-001 | INTERNACO SA | 000-P-MRQ-80012-001 | 000-P-MPO-50034-001 | Emergency Diesel Generators | 2019-02-27
MR-4131-001 | MR-4131-001 - LUBRICATION SYSTEMS COMPANY | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80012-001 - LUBRICATION SYSTEMS COMPANY | VENDOR DOCUMENTATION 000S- MR-4131-001 | LUBRICATION SYSTEMS COMPANY | 000-S-MRQ-80012-001 | 000-S-MPO-50019-001 | Oil Mist System | 2019-04-05
MR-4171-001 | MR-4171-001 - COES SRL | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80009-001 - COES SRL | VENDOR DOCUMENTATION 000S- MR-4171-001 | COES SRL | 000-S-MRQ-80009-001 | 000-S-MPO-50007 | Air Dryers | 2018-10-30
MR-4352-001 | MR-4352-001 - ENERSUL | JV-VD PACKAGE UNIT_OUT--- | 000-S-MRQ-80010-001 - ENERSUL | VENDOR DOCUMENTATION 000S- MR-4352-001 | ENERSUL | 000-S-MRQ-80010-001 | 000-S-MPO-50005-001 | BMP Sulphur Solidification Package | 2018-09-28

## Foglio1
SOC-JVD-VTRA-022841 | 2020-11-20 | 1 | V/P FOR RECIPROCATING COMPRESSOR (API 618) | stefania
SOC-JVD-VTRA-022842 | 2020-11-20 | 1 | V/P FOR HV POWER CAPACITOR BANKS | stefania
SOC-JVD-VTRA-022843 | 2020-11-20 | 1 | V/P FOR ELECTRONIC TRANSMITTERS | stefania
SOC-JVD-VTRA-022844 | 2020-11-20 | 1 | V/P FOR LV SWITCHGEARS | stefania
SOC-JVD-VTRA-022845 | 2020-11-20 | 1 | V/P FOR FAN & BLOWERS | stefania
SOC-JVD-VTRA-022846 | 2020-11-20 | 1 | V/P FOR ELECTRICAL HEAT TRACING | stefania
SOC-JVD-VTRA-022847 | 2020-11-20 | 1 | V/P FOR ELECTRICAL HEAT TRACING | stefania
SOC-JVD-VTRA-022848 | 2020-11-20 | 3 | V/P FOR LV SWITCHGEARS | OK ISSUED TO BAPCO WITH CON-BMP-VTRA-097677
SOC-JVD-VTRA-022849 | 2020-11-20 | 1 | V/P FOR ELECTROSTATIC COALESCER | stefania
SOC-JVD-VTRA-022850 | 2020-11-20 | 1 | V/P FOR SILENCERS (Process Silencer) | stefania
SOC-JVD-VTRA-022851 | 2020-11-20 | 1 | V/P FOR HV POWER CAPACITOR BANKS | stefania